## Sa2yanti Gantt
Week | Phase | Backend | Frontend | Deliverables | Status
Week 1 | Project Setup + Authentication | MongoDB + Structure + User Model + Register + Login + JWT + Validation | Structure + Login + Register + Auth Context + Protected Routes | Complete authentication system | Done
Week 2 | Orders System | Order Model + Create Order + Get Orders | Home + Create Order Form + My Orders | Create and track orders | Done
Week 3 | Technician System | Accept Order + Update Status | Technician Dashboard + My Jobs | Technicians manage orders
Week 4 | Services System | Service Model + Get Services | Services Page + Service Cards | Display services
Week 5 | Roles & Security | Role Middleware + Route Protection | Protected Pages by Role | Role-based system
Week 6 | UI Improvements | API improvements + fixes | Responsive + Loading + Empty States | Better UX
Week 7 | Testing | API Testing + Bug Fixes | Integration Testing | Stable system
Week 8 | Documentation & Delivery | Final review | Presentation + Documentation | Final submission